## Org Plan
| Effort | Topic | Topic Description | Sub topic/ Application | Type of K.O / Effort | Focus Market | Leader / Responsible | CofP Collaboration | Notas | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
1 | KO | Human Capital | Performance Competencies |  | Insight | PR | Paul | bar: 2026-03-01 to 2026-04-01
|  | Human Capital | Performance Competencies |  | PD | All | Andrea | bar: 2026-02-01 to 2026-03-01
| KO | Human Capital | Skills based organizations |  | Insight | All | Paul | bar: 2026-04-01 to 2026-05-01
| KO | Human Capital | Human Capital Framework | Maturity Assessment | Assessment tool | All | Mariam |  | Hacer ajustes a la rubrica y compartir; aqui hay oportunidad de foco externo usando a JPI como ejemplo | bar: 2026-02-01
|  | Human Capital | Capacidad | Case study incluyendo implementación (MARDOM) | External TBD and KC | All | Mariam |  | Foco en divulgación externa
|  | Human Capital | Talento | TNA | External TBD and KC | All | Mariam |  | Posibilidad de desarrollar el caso/PD
|  | Human Capital | Performance management |  | PD | All | Geral |  | Tenemos material en distintos lugares, hay que consolidar y ordenar
2 | KO | Leadership | Clima | ECO 2.0 | Assessment tool | All | Paul | bar: 2026-02-01 to 2026-03-01
|  | Leadership | Clima | ECO automation | App | All | Paul | Analytics | bar: 2026-03-01 to 2026-04-01
|  | Leadership | Cultura | Culture framework | Assessment tool | All | Paul/Lorraine |  | Terminar de definir framework y metodología | bar: 2026-03-01 to 2026-04-01
|  | Leadership | Cultura | Culturapp | App | All | Paul | Analytics | bar: 2026-04-01 to 2026-06-01
| KO | Leadership | Practicas de gestión | External TBC | Insight/Webinar | All | Paul | bar: 2026-07-01 to 2026-09-01
|  | Leadership | Leadership evaluation and development | Management evolution/reinvention | Insight | All | Paul | bar: 2026-05-01 to 2026-07-01
3 | KO | Future of work | Agentic AI adoption and management |  | Insight | All | Paul | Strategy | bar: 2026-09-01 to 2026-12-01

## Current topics (hidden)
Área / Pilar | Tema específico | Nivel | Priorizado | Due to | Responsable | Notas/ Próximos pasos | Ouput/Outcome
HC (Human Capital) | Org | 4 | No |  | GR
HC (Human Capital) | Compensación | 2 | No |  | —
HC (Human Capital) | Enablers | 0 | No |  | —
ECO | Improvements as product | 4 | No |  | PC | Foco en 2.0, mini ECO, y GPT
Change Management (CM) | CM (general) | 4 | No |  | PC | Mantener posts en social media
Other | Leadership development | 0 | No |  | PC | Management skills in the era of AI
Other | High-level org assessment | 0 | No |  | PC | Para diagnóstico rápido/GPT
HC (Human Capital) | Capacidad | 4 | Sí |  | MR | Foco en divulgarción externa
HC (Human Capital) | Competencias | 2 | Sí | Q2 | PC | Completar el PD
HC (Human Capital) | Talento | 2 | Sí |  | MR
HC (Human Capital) | Performance Management | 0 | Sí |  | GR | Tenemos material en distintos lugares, hay que consolidar y ordenar
HC (Human Capital) | Cultura | 1 | Sí | Q2 | PC | Terminar de definir framework y metodología
HC (Human Capital) | HC Maturity assessment | 1 | Sí | Q1 | PC | Hacer ajustes a la rubrica y compartir; aqui hay oportunidad de foco externo usando a JPI como ejemplo
Prácticas Gerenciales | Prácticas gerenciales | 4 | Sí | Q1 | PC | Foco en divulgarción externa
Other | Skills-based architectures | 0 | Sí |  | PC
Nivel de Maduréz
0 = Nada
1 = Framework
2 = Método
3 = Caso / PD
4 = KC / Training / Podcast / Webinar

## RD (hidden)
# | Insight | Industria foco | Trigger para el decision maker | Brecha organizacional | Producto / Servicio V2A asociado | Lead
1 | Automatizar sin rediseñar procesos: Riesgos de las zonas francas dominicanas | Zonas Francas | “Invertimos fuerte en tecnología, pero seguimos decidiendo igual” | Desalineación entre tecnología, roles y modelo de decisión | Diagnóstico Organizacional Integrado +Digital Transformation/Gestión del Cambio | Alfredo/ CoP DX/AI
2 | Capacitar para servir mejor, pero el sistema no acompaña | Turismo | “Entrenamos mucho, pero el servicio sigue siendo inconsistente” | Brecha entre capacitación, diseño del trabajo y prácticas gerenciales | HCMF/ Employee Experience / Clima aplicado a operación + Prácticas Gerenciales | Evaluar
3 | Cuando RRHH no diseña, el banco se vuelve lento | Sector Financiero | “Somos sólidos, pero cada cambio nos cuesta demasiado” | RRHH con rol operativo, no arquitecto de capacidades | HCMF + Diseño de Modelo de Gobernanza de Talento + Prácticas gerenciales | Alfredo/ Tati
4 | Transformar sin tocar cultura: por qué los grandes cambios fallan | Finanzas / Zonas Francas | “La estrategia está clara, pero la organización no cambia” | Cultura e incentivos no alineados con la transformación | HCMF / Cultural Assessment + Change Management End-to-End | Anibal

## Backlog (hidden)
Tema estratégico | Enfoque CoP | KO posibles | Prioridad | Due Quarter | Comentarios
Agentic Work & Operating Model Redesign | Rediseño organizacional humano-IA | Artículo flagship Framework de “Human–AI Operating Model” Metodología de diagnóstico ligero | Alta |  | Conecta HC + Cultura + CM. Diferenciador fuerte en PR/Caribe. Evitar hype técnico: foco organizacional.
Skills-Based Organizations | Talento Arquitecturas de capacidades | Artículo práctico Metodología para mapear skills vs trabajo Caso ilustrativo | Alta |  | Alineado con HC priorizado. Puede integrarse con Competency Model como producto.
Reinvención del rol del Manager | Prácticas gerenciales en era IA | Framework de “Manager-Coach” Toolkit de prácticas gerenciales Webinar / Training | Alta |  | Conectado con “Prácticas Gerenciales (4)”. Alto interés comercial.
Human Sustainability | Cultura + diseño del trabajo | Artículo de insight Marco conceptual (no wellness) Métricas de riesgo humano | Media |  | Riesgo estratégico, no clima/engagement.
Change Management para Perma-Change | Gestión de portafolios de cambio | Framework de “Change Portfolio” Metodología de capacidad de cambio | Media |  | Muy alineado con experiencia pública / descentralización. Menos sexy, muy útil.
US–Caribbean Nearshoring Models | Modelos operativos regionales | Artículo regional Caso Puerto Rico/ RD / Caribe | Baja |  | Valioso para posicionamiento regional, no core OD. Evitar dispersión.

## 2026 brainstorm
Category | Topic | Sub-topic/Applications | Knowledge Object | Q1 | Q2 | Q3 | Q4
Focus on things we can say we did or seen first hand - i.e use cases - not things we haven’t done
Human Capital | Competencies | [6 empty] | If Chat GPT can write better about it - its out
| Skills based orgs | [6 empty] | SEO optimized ahora es AI optimized --- que salga en el copilot summary del search ahora es mas impo
Desde el principio ESP y INGL siempre
| Human Capital Framework | HC Maturity assessment | [5 empty] | Usar templates and link to use case page for the web page
Leadership | Clima/Cultura/Practicas Gerenciales | ECO 2.0
Practicas Gerenciales
Culture Framework
| Leadership evaluation and development | Management evolution/reinvention
Future of Work | Agentic Work
Hecho
Iniciado
No de Org
Nuevo nuevo

## 2026 Quarterly Plan (hidden)
Quarter | Theme | Output | Maturity Level | Owner | Effort | Deliverable | Notes
Q1 (Jan-Mar) | Talent Architecture Foundation | Competencias PD | 2→3 (Method to Case) | PC leads, team documents | Medium | Internal PD completed | Front-load: Start Jan, complete by end Q1
|  | DR Financial Sector Insight - Draft | New → 1 (Framework) | DR team drafts, PC refines | Medium | Draft article for committee | Front-load: Kickoff Jan, carry into Q2
|  | Skills-Based Orgs - Framework kickoff | 0→1 (Framework development) | PC develops, DR/PR input | High | Initial framework outline | Front-load: 3-quarter journey (Q1-Q3)
|  | Social Media: Competency trends | Outreach | Team creates, PC approves | Low | 2 LinkedIn posts | Delegated, monthly cadence starts
Q2 (Apr-Jun) | Management & Leadership Evolution | Prácticas Gerenciales - Webinar/Training | 4 (Delivery mode) | PC delivers, team supports | Medium | 1 webinar OR 1 training | Leverage existing Level 4 content
|  | DR Financial Sector Insight - Published | 1 completed | Committee approves, team publishes | Low | Published article + promotion | Complete Q1 carryover
|  | Cultura Framework - Development | 1→2 (Framework to Method) | PC leads (70%), team supports | High | Draft methodology document | Intellectual work, carry to Q3 for testing
|  | Skills-Based Orgs - Methodology draft | 1→2 (Framework to Method) | PC develops, team researches | Medium | Draft skills mapping method | Quarter 2 of 3-quarter journey
|  | Social Media: Management evolution | Outreach | Team creates, PC approves | Low | 2 LinkedIn posts | Delegated, maintain cadence
Q3 (Jul-Sep) | Organization & Future of Work | DR Zonas Francas Insight - Draft | New → 1 (Framework) | DR team drafts, PC refines | Medium | Draft article for committee | Manage around summer surge; carry to Q4
|  | Cultura Framework - Client Testing | 2 validation (30% testing) | PC coordinates, team executes | Medium | Tested methodology + refinements | Complete Q2 carryover with pilot
|  | Skills-Based Orgs - Case development | 2→3 (Method to Case) | Team documents, PC guides | Medium | Illustrative case study | Quarter 3 of 3 - complete framework
|  | Agentic Work - Initial exploration | 0→1 (Early framework) | PC researches, team supports | Medium | Conceptual framework outline | Begin exploration for 2027
|  | Social Media: Future of work themes | Outreach | Team creates, PC approves | Low | 2 LinkedIn posts | Delegated, maintain cadence
Q4 (Oct-Dec) | Consolidation & Market Presence | DR Zonas Francas Insight - Published | 1 completed | Committee approves, team publishes | Low | Published article + promotion | Complete Q3 carryover
|  | Skills-Based Orgs - Webinar/Training | 3→4 (Delivery mode) | PC delivers, team supports | Medium | 1 webinar OR 1 training | Showcase completed framework
|  | Manager Reinvention - Framework kickoff | 0→1 (Framework) | PC develops, builds on Prácticas | Medium | Initial framework outline | Bridge to 2027, leverage Q2 insights
|  | HC Maturity Assessment - External case | Maintain 1, external positioning | PC leads, team develops | Medium | External case study/presentation | Use JPI or similar as example
|  | Year-end synthesis webinar | Outreach | PC presents, team organizes | Medium | Public webinar on OD trends | Thought leadership + lead generation
|  | Social Media: Year review + preview | Outreach | Team creates, PC approves | Low | 2 LinkedIn posts | Delegated, close year strong